## Main
Stake Holders |  |  |  | Remote Internship
Name | Role | Contact Number | Email ID | Grievance Management System
Ritesh Srivastava | Mentor | 9559661179 | ritesh.sri@tcs.com | Phase I
Apurva Tandon | Mentee | 8527681979 | apurvatandon@gmail.com | Phase II
Vartika Chowdhay | Mentee | 7897180125 | vartika_chowdhary@ymail.com | Phase III

## Phase_I
Project Phase I ( mention date)
Period | Frequency |  | Remarks/Purpose | Problems Statement / Challenges ( If Any)
Duration | Call Schedules | Mail Communication
Fortnight 1 | Every Wednesday | Every alternate day | Discussion upon Requirements and documentation
* Mention Dates for Phase 1 alone
Requirement Gathering
1st - 8th July 2016
Documentation
9th - 15th July 2016
Technology Involve
Office, Github
Progress Status / Action Plan
On-Time
Extended Support ( if Any )
Back to Main

## Phase_II
Project Phase II ( Mention dates )
Period | Frequency |  | Remarks/Purpose | Problems Statement / Challenges ( If Any)
Duration | Call Schedules | Mail Communication
Fortnight 2 | Every Wednesday | Every alternate day | Development of DB model & Prototypes
* Mention Dates for Phase II alone
Designing - DB
16th July - 22 July
Designing - Web (HTML) Prototypes
23rd July - 29th July
Technology Involve
MySQL, Netbeans JSP/HTML
Progress Status / Action Plan
On-Time
Extended Support ( if Any )
Connected with Mentor for DB modelling queries over weekend
Back to Main

## Phase_III
Project Phase III ( Mention dates )
Period | Frequency |  | Remarks/Purpose | Problems Statement / Challenges ( If Any)
Duration | Call Schedules | Mail Communication
Fortnight 3 | Every Wednesday | Every alternate day | Development of Server side code & acceptance testing
* Mention Dates for Phase III alone
Development
30th July - 10th Aug
Acceptance Testing
11th Aug - 12th Aug
Technology Involve
Chrome, Netbeans, Glassfish Server
Project Closure Status
Successfully Completed
Extended Support ( if Any )
Back to Main